## Review Managment Plan
Review ID | Review Comment | Action | Reviewee | Date | Reviewer | Status | comment
Rev_RevStr_01 | The review strategy is too simplified and process does not clear | Update the review process based on the feedback | Sahar | 2024-03-22 | Iternal review (team members) | Fixed
Rev_RevStr_02 | The responsabilities of the participants do not clear | Update the review process based on the feedback | Sahar | 2024-03-28 | Iternal review (team members) | Fixed
Rev_CHANGE _11 | The Change Management is too complicated and isn't clear | update the change management according to review | Amira | 2024-03-28 | Iternal review (team members) | Fixed

## SRS
Review ID | Review Comment | Action | Reviewee | Date | Reviewer | Status | comment
Rev_SRS_01 | The srs document needed approval after the initial fill | Updated upon the feedback | Yomna | 2024-03-22 | Iternal review (team members) | Fixed
Rev_SRS_02 | The srs document needed approval after writing some of the system features | Updated upon the feedback | Yomna | 2024-03-28 | Iternal review (team members) | Fixed
Rev_SRS_03 | The registration feature is written with a little details | The registration feature has been modified and updated with additional details. | Yomna | 2024-03-30 | Iternal review (team members) | Fixed
Rev_SRS_04 | The registration feature is written with a little details | The registration feature has been modified and updated with additional details. | Yomna | 2024-04-03 | Iternal review (team members) | Fixed
Rev_SRS_05 | The Rating system feature should not include words refer to design or ui element | Updated upon the feedback | Amira | 2024-04-04 | Iternal review (team members) | Fixed
Rev_SRS_06 | The Rating system feature should include clear msg | Updated upon the feedback the msg is clear | Amira | 2024-04-04 | Iternal review (team members) | Fixed
Rev_SRS_07 | The owner of the change should be mentioned in the Revision history tabl | Updated upon the feedback | Yomna | 2024-04-19 | Coach Esraa | Fixed

## Project Scope
Review ID | Review Comment | Action | Reviewee | Date | Reviewer | Status | comment
Rev_ProjScop_01 | The scope should contain the scope and out of scope of the project | Add the out of scope section in PMP | Sahar | 2024-03-28 | Iternal review (team members) | Fixed

## Communication
Review ID | Review Comment | Action | Reviewee | Date | Reviewer | Status | comment

## Risk Management
Review ID | Review Comment | Action | Reviewee | Date | Reviewer | Status | comment
Rev_Risk_10 | The Risk Management is too complicated and isn't clear | update the risk management according to review | Mariam Noureldin | 2024-03-28 | Iternal review (team members) | Fixed
Rev_Risk _13 | Risk Process is missing in PMP | Process Added | Mariam Noureldin | 2024-03-29 | Iternal review (team members) | Fixed
Rev_Risk _14 | Risk Register Details is missing in PMP | Risk Register Added | Mariam Noureldin | 2024-03-29 | Iternal review (team members) | Fixed
Rev_Risk _15 | Risk Analysis process is not clear in PMP | Process Updated | Mariam Noureldin | 2024-03-29 | Iternal review (team members) | Fixed

## RTM
Review ID | Review Comment | Action | Reviewee | Date | Reviewer | Status | comment
Rev_RTM_01 | The first column should be separated into two columns. one for siq and the other for customer requirements | columns separated according to review | Mariam | 2024-04-15 | Coach Esraa | Fixed
Rev_RTM_02 | SRS_Rtng_Fbk_3 doesn't have an upper linkage | SRS_Rtng_Fbk_3 link is done | Mariam | 2024-04-15 | Coach Esraa | Fixed
Rev_RTM_03 | Admin Features aren't linked | Admin Features links are done | Mariam | 2024-04-15 | Coach Esraa | Fixed

## Change Management
Review ID | Review Comment | Action | Reviewee | Date | Reviewer | Status | comment

## Problem Resolution
Review ID | Review Comment | Action | Reviewee | Date | Reviewer | Status | comment
Rev_Prob _01 | The Problem Resolution Management is too complicated and isn't clear | update the Problem Resolution according to review | Amira Hassan | 2024-03-28 | Iternal review (team members) | Fixed
Rev_Prob_02 | The Problem Management process only one technique should be choosen in Analysis | updated techniques | Amira Hassan | 2024-03-29 | Iternal review (team members) | Fixed
Rev_Prob_03 | problem identification prosess already include 5W-2H Technique | updated | Amira Hassan | 2024-03-29 | Iternal review (team members) | Fixed
Rev_Prob_04 | Define Priority criteria clearly | updated | Amira Hassan | 2024-03-30 | Iternal review (team members) | Fixed

## Revision History
Review ID | Review Comment | Action | Reviewee | Date | Reviewer | Status | comment
Rev_Histo _01 | revision history missing in pmp | created revision history in pmp | Amira Hassan | 2024-03-30 | Iternal review (team members)

## PMP DELIVERABLES
Review ID | Review Comment | Action | Reviewee | Date | Reviewer | Status | comment
Rev_PMP _01 | deliverables for week 2 is Missing in pmp | updated deliverables table in pmp | Amira Hassan | 2024-04-14 | Coach Esraa | Fixed

## CMP
Review ID | Review Comment | Action | Reviewee | Date | Reviewer | Status | comment | Review ID | Review Comment | Action | Reviewee | Date | Reviewer | Status | comment
Rev_CMP_01 | Configuration Managment Plan is more detailed in Branching and Merging Section | Process Updated | Esraa Mustafa | 2024-03-29 | Iternal review (team members) | Fixed
Rev_CMP_02 | Baseline strategy in 4 steps instead of questions ( who - when - How ) | Process Updated | Esraa Mustafa | 2024-03-30 | Iternal review (team members) | Fixed

## CM Tool
Review ID | Review Comment | Action | Reviewee | Date | Reviewer | Status | comment
Rev_CM _01 | The comment when we upload file on github is too short and not clear it should contains more details | will work on it | Amira | 2024-03-30 | Eng Mohamed Hassan | Open